## Sheet1
Team Members
[5 empty] | First Name | Last Name | Student ID
[5 empty] | Domat | Al Khoury | 40246644
[5 empty] | Rawda | Waez | 40139173
[5 empty] | Elias | Hannoun | 40246643
[5 empty] | Caline | Batal | 40250222
[5 empty] | Mohammed | Al Assad | 40252007
[5 empty] | Abdelmalek | Mouhamou | 40250222
Activities Table
Date | Type of Activty | Purpose | Hours spent
|  |  | Domat | Rawda | Elias | Caline | Mohammed | Abdelmalek
2024-02-24 | Lab Meeting | Discuss the steps to be taken for Sprint 2 and divide work between team members. | 1 | 1 | 1 | 1 | 1 | 1
2024-02-25 | Online Meeting | Discuss the implementation of backend functionality. | 1 | 0 | 0 | 0 | 1 | 1
2024-02-26 | Online Meeting | Discuss the implementation of frontend functionality. | 0 | 1 | 1 | 1 | 0 | 0
2024-02-27 | Online Meeting | Start the implementation of the frontend. | 0 | 1 | 1 | 1 | 0 | 0
2024-03-01 | Online Meeting | Modify the backend to match the frontend requirements. | 1 | 0 | 0 | 0 | 1 | 1
2024-03-03 | Online Meeting | Continue working on frontend. | 0 | 1 | 1 | 1 | 0 | 0
2024-03-06 | Online Meeting | Connecting frontend with backend. | 1 | 1 | 1 | 1 | 0 | 0
2024-03-09 | Online Meeting | Write tests for backend. | 0 | 0 | 0 | 0 | 1 | 1
2024-03-10 | Online Meeting | Finalize the frontend. | 0 | 1 | 1 | 1 | 0 | 0
2024-03-11 | Online Meeting | Finalize the project. | 2 | 2 | 2 | 2 | 2 | 2